## Progress claim
Fill in the shaded cells. Every total works itself out. Amounts are ex GST until the GST line.
From (you) |  |  | To (client or head contractor)
Business name |  |  | Name
ABN |  |  | ABN (if a business)
Licence number |  |  | Address
Address |  |  | Email
Phone
Email
Claim details
Claim number |  |  | Project or site address
Claim date |  |  | Contract or quote reference
Work up to (reference date) |  |  | Contract date
Payment due date |  |  | Payment terms
Stages in the contract
Stage or work done | Contract value (ex GST) | % complete to date | Value completed to date | Previously claimed (ex GST) | This claim (ex GST)
Stage totals
Approved variations (only ones the client agreed in writing)
Variation number and description | Approved amount (ex GST) | % complete to date | Value completed to date | Previously claimed (ex GST) | This claim (ex GST)
Variation totals
Summary
Original contract sum (ex GST)
Approved variations (ex GST)
Revised contract sum (ex GST)
Work completed to date, stages plus variations (ex GST)
Less retention held (only if your contract allows it) |  |  |  |  | 0
Less amounts previously claimed (ex GST)
This claim (ex GST)
GST at 10%
Are you registered for GST? (Yes or No - No removes the GST and the words "tax invoice") |  |  |  |  | Yes
AMOUNT DUE FOR THIS CLAIM (inc GST)
How to pay
Account name |  |  | BSB
Account number |  |  | Payment reference
Statement (only if your state's Act or your contract asks for it)
This is a payment claim made under the [name of your state's security of payment Act].
See the How to use tab for what NSW, Queensland, Victoria and WA say, with links. Delete the statement line if your state and contract do not need it.
Free template from TrackYaTradie (trackyatradie.com). General information only, not legal advice. Progress claim rules differ by state: check with your state's regulator before you rely on a claim.

## Example
Fill in the shaded cells. Every total works itself out. Amounts are ex GST until the GST line.
From (you) |  |  | To (client or head contractor)
Business name | Your business name |  | Name | Client name
ABN | 00 000 000 000 |  | ABN (if a business)
Licence number | Your licence number |  | Address | 10 Sample Road, Suburb STATE 0000
Address | 1 Example Street, Suburb STATE 0000 |  | Email | client@example.com
Phone | 0400 000 000
Email | you@example.com
Claim details
Claim number | 2 |  | Project or site address | 10 Sample Road renovation
Claim date | 2026-10-30 |  | Contract or quote reference | Quote Q-1042
Work up to (reference date) | 2026-10-30 |  | Contract date | 2026-09-01
Payment due date | 2026-11-06 |  | Payment terms | 7 days
Stages in the contract
Stage or work done | Contract value (ex GST) | % complete to date | Value completed to date | Previously claimed (ex GST) | This claim (ex GST)
Deposit (contract signed) | 2000 | 100% |  | 2000
Frame up | 12000 | 100% |  | 0
Lock-up | 16000 | 0% |  | 0
Practical completion | 10000 | 0% |  | 0
Stage totals
Approved variations (only ones the client agreed in writing)
Variation number and description | Approved amount (ex GST) | % complete to date | Value completed to date | Previously claimed (ex GST) | This claim (ex GST)
V1: extra bracing to rear wall | 1850 | 100% |  | 0
Variation totals
Summary
Original contract sum (ex GST)
Approved variations (ex GST)
Revised contract sum (ex GST)
Work completed to date, stages plus variations (ex GST)
Less retention held (only if your contract allows it) |  |  |  |  | 0
Less amounts previously claimed (ex GST)
This claim (ex GST)
GST at 10%
Are you registered for GST? (Yes or No - No removes the GST and the words "tax invoice") |  |  |  |  | Yes
AMOUNT DUE FOR THIS CLAIM (inc GST)
How to pay
Account name | Your business name |  | BSB | 000-000
Account number | 00000000 |  | Payment reference | Claim 2
Statement (only if your state's Act or your contract asks for it)
This is a payment claim made under the [name of your state's security of payment Act].
See the How to use tab for what NSW, Queensland, Victoria and WA say, with links. Delete the statement line if your state and contract do not need it.
Free template from TrackYaTradie (trackyatradie.com). General information only, not legal advice. Progress claim rules differ by state: check with your state's regulator before you rely on a claim.

## How to use
How to use this progress claim template
Filling it in
1 | Fill in your details and the client's details once. Save a copy for each new claim on the job.
2 | List the stages from your quote or contract with their value ex GST. Use the same stage names the client agreed to.
3 | Enter the % complete to date for each stage, and what you have already claimed for it. The sheet works out the value done and this claim.
4 | Add each approved variation as its own line. Only include variations the client agreed in writing, and keep them separate from the stages.
5 | Set "Registered for GST?" to Yes or No. Yes adds 10% GST and titles the claim a tax invoice. No removes both.
6 | Fill in how to pay and the payment due date, then save as PDF and send it in writing to the person your contract names.
7 | Keep a record of when they received it, and attach photos or a short note of the work done if that helps them say yes.
GST and tax invoices
If you are registered for GST, each progress claim is a tax invoice. The ATO lists what a tax invoice must show, including the words "tax invoice", your business name and ABN, the date, what you supplied and the GST. For sales of $1,000 or more it must also show the buyer's identity or ABN.
State notes (checked October 2026 - always read your own state's current page)
NSW | Claims are made on or after the reference date in the contract, or the last day of each month if there is none. One claim per reference date, for work in the past 12 months. Subcontractors on work connected with a residential construction contract must include the statement "This is a payment claim made under the Building and Construction Industry Security of Payment Act 1999 NSW". Head contractors must include a supporting statement. https://www.nsw.gov.au/housing-and-construction/compliance-and-regulation/security-of-payment/making-a-payment-claim
QLD | A payment claim must identify the work, state the amount claimed and request payment of it. There is no prescribed format. The reference date is the date in your contract, or the last day of the month the work was done if the contract has none, and only one claim can be given for each reference date. https://www.qbcc.qld.gov.au/running-business/getting-paid/request-payment
VIC | The Building and Construction Industry Security of Payment Act 2002 has new versions from 15 April and 24 June 2026. Make sure any template, checklist or advice you use matches the current Act. https://www.legislation.vic.gov.au/in-force/acts/building-and-construction-industry-security-payment-act-2002
WA | The Building and Construction Industry (Security of Payment) Act 2021 covers contracts entered into on or after 1 August 2022. A claim to a homeowner needs a homeowner's notice attached. Building and Energy publishes its own template payment claim and user guide. https://www.wa.gov.au/government/multi-step-guides/subcontractor-payment-disputes-security-of-payment-act/making-payment-claim
SA, TAS, ACT, NT | Each has its own security of payment Act with its own rules for what a claim must say and when it can be made. Read your Act and your regulator's guidance before you serve a claim you intend to enforce.
Not legal advice
This template is general information only. Check with your state's regulator, or a lawyer, before you rely on a claim under your state's Act.
Tracking claims across jobs
TrackYaTradie splits a job into payment stages, shows what has been paid and what is owing, and sends each claim from your phone. Free trial: https://trackyatradie.com